## Sheet1
Gantt Chart Template
Project Name: Insert project name
Project Manager: Insert name and contact details of project manager
Project Dates: Insert project start and end dates
Task Title | Start Date | End Date | Duration | Assigned | Progress | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3
[6 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Business need | 2025-09-14 | 2025-09-16 | 2 | bar: Week 1 M to Week 1 W
High-level requirements | 2025-09-17 | 2025-09-18 | 1 | bar: Week 1 T to Week 1 F
Objectives | 2025-09-21 | 2025-09-23 | 2 | bar: Week 2 M to Week 2 W
Project team | 2025-09-24 | 2025-09-25 | 1 | bar: Week 2 T to Week 2 F
Risk assessment | 2025-09-28 | 2025-09-29 | 1 | bar: Week 3 M to Week 3 T
Scope | 2025-09-30 | 2025-09-30 | 0 | bar: Week 3 W to Week 3 T
Success Criteria | 2025-10-02 | 2025-10-02 | 0 | bar: Week 3 F

## Sheet1 (2)
Gantt Chart Template
Project Name: | Benji's Project
Project Manager: Insert name and contact details of project manager
Project Dates: Insert project start and end dates
Task Title | Start Date | Duration | End Date | Adjusted Length | Assigned | Progress
Business need | 2025-09-17 | 5 | 2025-09-24 | 7
High-level requirements | 2025-09-17 | 4 | 2025-09-23 | 6
Objectives | 2025-09-21 | 2 | 2025-09-23 | 2
Project team | 2025-09-24 | 3 | 2025-09-29 | 5
Risk assessment | 2025-09-28 | 2 | 2025-09-30 | 2
Scope | 2025-09-30 | 3 | 2025-10-03 | 3
Success Criteria | 2025-10-02 | 2 | 2025-10-06 | 4
Formulas:
End Date = WORKDAY([Start Date],[Duration])